## Ark1
Beginning |  | 2024-01-08
End |  | 2024-06-04
| Activity |  | UKE
|  |  | January |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  |  | June
|  |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
| Preperation | Specify the problem statement | bar: January 5
Gantt-diagram | bar: January 4
Mid-term presentation | bar: March 11
Hyvalue days - not attended | bar: May 19
| Research | Hydrogen | bar: January 5 to February 8; May 19
Offshore and onshore | bar: January 5 to March 10; May 19
Electrolyser | bar: February 8 to March 10; May 19
Study areas | bar: February 6 to February 7; May 19
Transport methods | bar: February 8 to March 11; May 19
Economy | bar: February 9 to March 11; May 19 to May 20
| Writing process | Preface
Abstract | bar: May 21
Introduction | bar: February 9 to March 11
Method | bar: April 14 to May 20
Results | bar: March 12 to May 21
Discussion | bar: March 11 to May 21
Conclusion | bar: April 14 to May 21
| Completion | Spelling and proofreading | bar: May 18 to May 21
Review of sources and attachments | bar: May 18 to May 21
Checklist | bar: May 18 to May 21
Submit to supervisor | bar: May 18 to May 21
Review feedback from supervisor | bar: May 20
| Finalise | Checklist | bar: May 20
|  | Submit the report | May 21: 2024-05-21
|  | Oral exam | June 23: 2024-06-04
Important dates | bar: January 3
Critical | bar: January 3
Almost critical | bar: January 3
|  | Proposed date for latest submission of the assignment | January 3: 2024-05-13